## Progress Summary
Report Summary | Status
Module / Sub Module | Development Completed | Development Inprogress | Requirement Pending | Grand Total
Finance | 21 | 1 | 2 | 24
(blank) | 21 | 1 | 2 | 24
SCM | 14 | 1 |  | 15
(blank) | 14 | 1 |  | 15
Grand Total | 35 | 2 | 2 | 39

## Progress Detail
Sl No | Component ID | Task Name | Module | Sub Module | Priority | Priority Sequence | Go-Live Critical | Type | Development Resource | Testing Resource | Status | Priority Num | Milestone | MD50 | Planned Start Date | Planned Completion Date | Delivered Date | Feedback Received Date | Actual Completion Date2 | Completion % | Doc Received Date | Springboard Folders
1 |  | Cheque Printing | Finance |  | P1 |  | Yes | BI Publisher | Varsha Kathikeyan | Jagadees | Development Completed |  |  | Yes | [7 empty] | used EBS layouts
2 |  | Wire Transfer advise printing | Finance |  | P1 |  | Yes | BI Publisher | Varsha Kathikeyan | Jagadees | Development Completed |  |  | Yes
3 |  | AR Tax invoice printing | Finance |  | P1 |  | Yes | BI Publisher | Varsha Kathikeyan | Jagadees | Development Completed |  |  | Yes | 2022-08-01 | 2022-08-03
4 |  | AR Tax Credit note printing | Finance |  | P1 |  | Yes | BI Publisher | Maria Lawrance K | Jagadees | Development Completed |  |  | Yes | 2022-08-01 | 2022-08-03
5 |  | AR Receipt Acknowledgment Printing(AR Receipt Report) | Finance |  | P1 |  | Yes | BI Publisher | Varsha Kathikeyan | Jagadees | Development Completed | Development Completed | Development Completed | Yes | [7 empty] | AR
6 |  | VAT Sales Register | Finance |  | P1 |  | Yes | BI Publisher | Varsha Kathikeyan | Jagadees | Development Completed |  |  | Yes | [7 empty] | VAT Folder
7 |  | VAT Purchase Register | Finance |  | P1 |  | Yes | BI Publisher | Maria Lawrance K | Jagadees | Development Completed |  |  | Yes | [7 empty] | VAT Folder
8 |  | Supplier Statement | Finance |  | P2 |  | Yes | BI Publisher | Varsha Kathikeyan | Jagadees | Development Completed |  |  | Yes | [7 empty] | AP
9 |  | Customer Statement | Finance |  | P2 |  | Yes | BI Publisher | Maria Lawrance K | Jagadees | Development Completed |  |  | Yes | [7 empty] | AR
10 |  | Related Party Combined AP/AR Report | Finance |  | P2 |  | Yes | BI Publisher |  | Jagadees | Development Inprogress | [10 empty] | GL
11 |  | FA Register | Finance |  | P2 |  | Yes | BI Publisher | Varsha Kathikeyan | Jagadees | Development Completed |  |  | Yes | [7 empty] | FA
12 |  | Project related Legal case report | Finance |  | P2 |  | Yes | BI Publisher |  | Krishna | Requirement Pending | [10 empty] | GL
13 |  | Purchase Order report | SCM |  | P1 | 1 | Yes | BI Publisher | Varsha Kathikeyan | Cyril Joshua | Development Completed |  |  | Yes | 2022-07-26 | 2022-07-28 |  |  |  |  | 2022-07-25
14 |  | Procure to Pay Report | SCM |  | P1 | 2 | Yes | BI Publisher | Maria Lawrance K | Cyril Joshua | Development Completed |  |  | Yes | 2022-08-03 | 2022-08-05
15 |  | Maintenance Work order Cost report | SCM |  | P1 | 3 | Yes | BI Publisher | Maria Lawrance K | Cyril Joshua | Development Completed |  |  | Yes
16 |  | Maintenance Material Detail Report | SCM |  | P1 | 4 | Yes | BI Publisher | Varsha Kathikeyan | Cyril Joshua | Development Completed |  |  | Yes | 2022-08-03 | 2022-08-05
17 |  | Quotation Analysis Report | SCM |  | P1 | 5 | Yes | BI Publisher | Varsha Kathikeyan | Cyril Joshua | Development Completed |  |  | Yes
18 |  | Inventory stock Movement Report | SCM |  | P1 | 6 | Yes | BI Publisher | Varsha Kathikeyan | Cyril Joshua | Development Completed |  |  | Yes
19 |  | Supplier Listing Report | SCM |  | P1 | 7 | Yes | BI Publisher | Maria Lawrance K | Cyril Joshua | Development Completed |  |  | Yes
20 |  | Supplier Balance Summary | Finance |  | P1 |  | Yes | BI Publisher | Maria Lawrance K | Jagadees | Development Completed |  |  | Yes | [7 empty] | AP
21 |  | Customer Balance Summary | Finance |  | P1 |  | Yes | BI Publisher | Varsha Kathikeyan | Jagadees | Development Completed |  |  | Yes | [7 empty] | AR
22 |  | Store Issue Voucher Report | SCM |  | P1 |  | Yes | BI Publisher | Varsha Kathikeyan | Cyril Joshua | Development Completed |  |  | Yes
23 |  | Store Receipt Voucher Report | SCM |  | P1 |  | Yes | BI Publisher | Maria Lawrance K | Cyril Joshua | Development Completed |  |  | Yes
24 |  | Supply Agreement Report | SCM |  | P1 |  | Yes | BI Publisher | Maria Lawrance K | Cyril Joshua | Development Completed |  |  | Yes
25 |  | SERVICE PROVIDER AGREEMENT REPORT | SCM |  | P1 |  | Yes | BI Publisher | Maria Lawrance K | Cyril Joshua | Development Completed |  |  | Yes
26 |  | Inventory OnHand report | SCM |  | P1 |  | Yes | BI Publisher | Maria Lawrance K | Cyril Joshua | Development Completed |  |  | No
27 |  | RFQ Supplier copy repoC35:M36rt(Seeded) | SCM |  | P1 |  | Yes | BI Publisher | Varsha Kathikeyan | Cyril Joshua | Development Completed |  |  | Yes
28 |  | Purchase Order Summary Report | SCM |  | P1 |  | Yes | BI Publisher | Varsha Kathikeyan | Cyril Joshua | Development Completed |  |  | No
29 |  | AR Unearned Revenue Balance Report | Finance |  | P1 |  | No | BI Publisher | Arunpndian | Jagadees | Development Completed |  |  | Yes | 2022-11-19
30 |  | AHG Reference Reconciliation Report | Finance |  | P1 |  | No | BI Publisher | Varsha Kathikeyan | Jagadees | Development Completed
31 |  | AP Prepaid Unamortized Balance Report | Finance |  | P1 |  |  | BI Publisher | Arunpandian | Jagadees | Development Completed
32 |  | Detailed Balance sheet | Finance |  | P1 |  |  | FRS | Arunpandian | Jagadees | Development Completed
33 |  | Profit and Loss Account | Finance |  | P1 |  |  | FRS | Arunpandian | Jagadees | Development Completed
34 |  | KAH Family TB | Finance |  | P1 |  |  | FRS | Arunpandian | Jagadees | Development Completed
35 |  | ORE Detail Mnth HK | Finance |  | P1 |  |  | FRS | Arunpandian | Jagadees | Development Completed
36 |  | Balances Bank/Loan/FD_HK | Finance |  | P1 |  |  | FRS | Arunpandian | Jagadees | Development Completed
37 |  | Project Summary Report | Finance |  | P1 |  |  | OTBI | Arunpandian | Jagadees | Development Completed
38 |  | AR Related Details | Audit |  | P1 |  |  | BI Publisher | Varsha Kathikeyan | Jagadees | Development Inprogress
39 |  | Bank Reconcilation Related Details | Audit |  | P1 |  |  | BI Publisher | Varsha Kathikeyan | Jagadees | Development Inprogress
40 |  | Purchase Order Details | Audit |  | P1 |  |  | BI Publisher | Varsha Kathikeyan | Cyril Joshua | Development Inprogress
41 |  | Work Order Details | Audit |  | P1 |  |  | BI Publisher | Varsha Kathikeyan | Cyril Joshua | Development Inprogress
42 |  | PR View PDF Report | SCM |  | P1 |  |  | BI Publisher | Arunpandian | Cyril Joshua | Development Inprogress
43 |  | Advance/Prepayment Balance Report | Finance |  | P1 |  |  | BI Publisher |  | Jagadees | Requirement Pending

## Data
Resource | Status | Module | Sub Module | Technology | EBS / Fusion | Priority | Dev. Mode | Go-Live Critical | Phase | Type
Maria Lawrance K | Awaiting Client Confirmation | Finance | Accounts Payable | Report | EBS | P1 | Offshore | Yes | Development | BI Publisher
Cyril Joshua | Awaiting Functional Feedback | SCM | Accounts Receivables |  | SAAS | P2 | Onsite | No | Support | OTBI
Jagadees | Awaiting Functional Clarification | Project | Fixed Assets |  | OBIEE | P3 |  |  |  | Integration
Varsha Kathikeyan | Cancelled | HCM | Cash Management | [6 empty] | Notification
Ashwini L | Development Completed | OTM | General Ledger | [6 empty] | FRS
Arunpandian | Development Inprogress | Custom | Inventory |  |  | 1
Mithun | Development Pending | CX Sales | Order Management |  |  | 2
Krishna | Hold | OTBI | Procurement |  |  | 3
| Implemented | Audit | Sourcing |  |  | 4
| Requirement Pending |  | Work In Process |  |  | 5
| Rework Inprocess - CR |  | Project Accounting |  |  | 6
| Rework Inprocess - IR |  | HR |  |  | 7
| Rework Pending - CR |  | Payroll
| Rework Pending - IR |  | Absence
| Task Completed |  | Manufacturing
| Vendor Support |  | Quality
| Sync Development Completed |  | OTL
| Req Document to be updated |  | Learning
| Internal Testing |  | Recruitment
| Completed - Partial input pending |  | Compensation
Benefits
Fixed Asset

## CR History
Component ID | Module | Report Name | Feedback Received Date | Functional Comments | Techical Resource | Start Date | Completion Date | Status